## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2251-swen-261-05-6 Group 6
Testing Team Name | 2251-swen-261-05-7

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a user, I want to log into the service so that I can use the service while maintaining my data. | **Given** I'm a U-Fund manager **when** I log in **then** I expect to be logged in as an admin. | Pass | TS; 10/21 | Pass | ARP
| **Given** I'm a helper **when** I log in with my username **then** I expect to be logged in as a helper | Pass | TS; 10/21 | Pass | ARP
| **Given** I'm a new user **when** I log in **then** I expect a new account to be created and myself to be logged in. | Pass | TS; 10/21 | Pass | ARP
As a user, I want to log out so that nobody else can access my account. | **Given** I am logged in **when** I click the log out button **then** I should be logged out. | Pass | TS; 10/21 | Pass | ARP
As a UFUND MANAGER I want to see options to edit and remove I need so that I can keep my needs up to date. | Given I am a manager when I select the edit button then I should be prompted with a way to edit the need | Pass | CR; 10/21; Also needs a create need button, but made that a new story so more tests can be done | Pass | PLM
| Given I am a manager when I select the delete need button then the need should be removed from the cupboard | Pass | CR; 10/21 | Pass | PLM
| Given I am a user when I am on the cupboard page then I should not see any admin buttons | Pass | CR; 10/21 | Pass | PLM
As a User, I want to be able to see all the needs in the cupboard so I can pick which ones to add to my basket | Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket. | Pass | CR; 10/22 | Pass | PLM
| Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description. | Pass | CR; 10/22 | Pass | PLM
As a User I want to have a separate login so the admin cannot see my personal basket | Given I am on the cupboard page when I attempt to search for a need then any matching needs should appear | Pass | CR; 10/22 | Pass | PLM - Beginin spaces are not trucated in search - pressing "enter" key in search bar does not search
| Given I am on the cupboard page when I attempt to search for a need that does not exist then no needs should appear | Pass | CR; 10/22 | Pass | PLM
As a UFUND MANAGER I want to see an option to create a need so that I can make new needs visible to helpers. | Given I am a manager when I select the create need button then I should be prompted with a way to create a new need | Pass | MM; 10/22 | Pass | PLM - Creating a need when searching adds the need to the list even if it doesn't match the search
| Given I am a helper when I am looking at the cupboard then I should not see the create need button | Pass | MM; 10/22 | Pass | PLM
As a User I want to be able to view all the needs in my basket to confirm That they have what they want to support | Given I am logged in as a user, when I am on the main page, then I expect to see a way to get to my basket | Pass | MM; 10/22 | Pass | PLM
| Given I am logged in as an admin, when I am on the main page, then I should not see a basket | Pass | MM; 10/22 | Pass | PLM
As a User I want to open the basket so I can utilize the basket. | Given Im a HELPER when I open my basket I expect to see the needs I added | Pass | MM; 10/22 | Pass | PLM
As a user I need to have a checkout so funding can get added to needs. | **Given** I'm a HELPER **when** I go to checkout **then** I expect to be able to purchase the needs in there cart. | Pass | KL; 10/22 | Fail | PLM - Needs sometimes aren't added to the basket (Probably becaus ethey are resolved but still shop up in the cupboard)
| **Given** I'm a helper **when** I don't have any needs filled **then** I expect to not be able to checkout. | Pass | KL; 10/22 | Fail | PLM - I am not stoped from checking out when my needs are empty or invalid (ex: negative value in count)
| Given I am a helper when I checkout then the needs should be fulfilled | Pass | KL; 10/22 | Fail | PLM Fullfilled needs still apear in the cupboard
As a helper I want to see options add a need to my basket so that I can checkout. | As a helper I can select a specific amount of a need and add that amount to my basket | Pass | KL; 10/22 | Pass | PLM
As a user I want to edit my counts in my basket so I can ensure I only have the amount of needs I want in my basket. | Given I am a user, when I go to my basket then I should see a way to edit the count of each need in my basket |  |  | Pass | PLM - I can manually put negative values, they get removed only when I reload the basket
As a user, I want to be able to talk with an AI chatbot so that I can learn more about bees and get fun facts about bees | Given I am a user on the cupboard page, when I view the page, then I should see some way to access the chatbot |  |  | Pass | CR; 11/9
| Given I am a user with the AI chatbot open, when I send a message to the AI, then I expect to see a response to my message from the AI. |  |  | Pass | CR; 11/9
As a user I want to be able to change personalities on my chatbot so that I can get a more personalized chat experience. | Given that I am a logged in user, when I open the chat I should be prompted with a personality to select. |  |  | Pass | CR; 11/9
| Given that I select a personality, when I chat with my selected personality, I should be provided the according chat experience. |  |  | Pass | CR; 11/9
As a user, I want the display for the needs in the cupboard to look visually appealing and easy to use so I can enjoy the look and have ease of user | Given I am logged in as a helper, when I am on the cupboard page, then I should be able to see a way to add needs to my basket |  |  | Pass | CR; 11/11
| Given I am logged in as a helper, when I am on the cupboard page then I should be able to tell how many of a need I am adding to my basket |  |  | Pass | CR; 11/11
As a User, I want the header to look better so I can easily navigate the page | Given that I am a user, when I click on the basket, then it should be Bee-themed, so it matches the theme. |  |  | Pass | CR; 11/11
As a USER I want to press the log in button so that the username and password forms show up in an overlay. | Given I am not logged in when I hit the log in button then a way to log in with a username and password |  |  | Pass | MM; 10/22
| Given I am not logged in, when I try to log in, then a way to enter my security questions should be present |  |  | Pass | MM; 10/22
| Given I am not logged in and restricted, when i try to log in, then i should be told i am restricted and unable to login |  |  | Pass | MM; 10/22
As a USER I want to look at a cool basket so that my experieince is better. | Given I am on the main page, when I look at the header then I should be able to easily navigate it |  |  | Pass | CR; 11/11
As a Developer I want to store user security questions so that the API can verify user password recovery. | Given I am a user who has forgotten my password, when I hit the forgot password button, then I expect to see a security question |  |  | Pass | KL; 10/22
| Given I am a user who has forgotten my password, when I answer the security question incorrectly, I should not be able to make a new password |  |  | Pass | KL; 10/22
| Given I am a user who has forgotten my password, when I answer the security question correctly, I should be able to make a new password |  |  | Pass | KL; 10/22
As a User I want to be able to return to the website while me session is valid and stay logged in so that I need to login less often. | Given I am logged in, when I refresh the page then I should stay logged in |  |  | Pass | CR; 11/11
| Given I am a user, when I leave the site and then return then I should stay logged in |  |  | Pass | CR; 11/11
As a Helper I want to be able to edit my account via the website so that I can manually change my username / password using the UI. | Given I am a helper, when I attempt to change my information then I should only be able to change my username |  |  | Pass | MM; 10/22
| Given I am a helper, when I successfully edit my account then I should be logged out and my session should be invalidated |  |  | Pass | MM; 10/22
As a Admin I want to be able to edit any account via the website so that I can manually change users using UI. | Given I am an admin, when I attempt to change a users information then it should be reflected on their account |  |  | Pass | MM; 10/22
| Given I am a user whose account information has ben changed, when I access my account, then the changes should be reflected |  |  | Pass | MM; 10/22
Extra bugs: - Quantity can be negative & decimal - Cost can be negative and in less than the hundredth place ex(1.003$) - Words with no spaces in descriptions/tittles go out of the box instead of warping - Spaces at the start of search are not trucated - Buttons that shouldn't be pressable (ex: logout, delete,...) are still pressable when popups are open - Basket remains open if loging out while it is open - Invalid values aren't changed in the frontend unless the popup or page is reloaded